## Stakeholder Analysis 2 (hidden)
Stakeholder Analysis
Name | Department / Company | Position | Advisers | Objectives, Requirements, Interests | Influence | Project Contribution | Resistance
Pet Owners | User | Customer |  | Expects a hassle-free booking experience and trusted service providers. | High | Uses the platform, provides feedback, and generates revenue. | Preference for traditional booking methods and lack of trust in new platforms.
Pet Service Provider | User | Client |  | Expects increased sales from successful bookings, better market exposure, and comprehensible sales reports. | High | Offers services, provides feedback, and generates revenue. | Preference for traditional booking methods and lack of trust in new platforms.
Lalainne Andaya | Management | Project Manager/Team Lead | Developers, QA, Release Manager, Marketing & Sales Team, and Project Adivser and Consultant | Successfully deliver the project on time while achieving the project's objectives, and effectively communicate and manage the team. | High | Leads the team, helps in strategic planning, identifies risks, and monitors the team. | Unrealistic deadlines, limited budget, and poor communication with the team.
Atasha Frances Gayle Doria | Dev Team | Lead Developer | Project Manager, Release Manager, Project Adviser, & Project Consultant | Develop a system that passes all the acceptance criteria and effectively collaborate with the team. | High | Develops and leads the development, testing, and deployment of the platform. | Unclear requirements, lack of time for development, limited budget, and poor communication with the team.
Michelle Reina Pineda | Testing Team | Lead Quality Assurance | Project Manager, Release Manager, Project Adviser, & Project Consultant | Ensure the system is bug-free and meets all requirements. | High | Leads and performs system testing. | Unclear acceptance criteria, lack of time for thorough testing, limited budget, and poor communication with the team.
Feliz Angelica Salting | Management | Release Manager | Project Manager, Release Manager, Project Adviser, & Project Consultant | Minimize risk during release and ensure on-time deployment of the system, along with necessary documentation. | High | Provides and coordinates the platform's release information. | Last-minute changes, limited budget, and poor communication with the team.
Developers | Dev Team | Frontend and Backend Developers | Lead Developer, Project Manager, Release Manager, Project Adviser, & Project Consultant | Develop the system's features and meet all technical goals. | High | Develops, tests, and deploys the frontend and backend of the system. | Unclear requirements, limited budget for development, technical challenges with minimal development time, and poor communication with the team.
Mr. Carl Dominique Bueno | Asia Pacific College | Project Adviser |  | Guide the students towards successful project completion. | High | Guides the Project Manager, Developers, and Release Manager in each SDLC phase. | Team's lack of technical experience.
Mr. Porfirio Atienza | Asia Pacific College | Project Consultant |  | Guides the student towards successful project completion, specifically within their area of expertise. | Medium | Provides specific support for the team, mainly in diagram creation and system development. | Team's lack of technical experience.
Mr. Bary Reyes | Asia Pacific College | Project Consultant |  | Guides the student towards successful project completion, specifically within their area of expertise. | Medium | Provides specific support for the team, mainly in sprint and system testing. | Team's lack of technical experience.
Mr. Rhea-Luz Valbuena | Asia Pacific College | Project Consultant |  | Guides the student towards successful project completion, specifically within their area of expertise. | Medium | Provides specific support for the team, mainly in analyzing the data. | Team's lack of technical experience.
Marketing & Sales Team |  | Marketing Researcher/ Social Media Manager | Project Manager, Release Manager, Dev Team and Project Adviser and Consultant | Successfully market the system to the target audience and find beta testers for the system. | Medium | Helps the team to promote the system on social media and to its target market. | Limited budget for marketing.
Competitors |  | External Influence |  | Continuously compete in the growing market, providing opportunities for innovation. | Low | Pushes the team to innovate and provide a better experience to users. | Established market presence with ample resources.

## Stakeholder Analysis
Stakeholder Analysis
Name | Department / Company | Position | Advisers | Objectives, Requirements, Interests | Influence | Project Contribution | Resistance
Pet Owners | User | Client |  | Expects a hassle-free booking experience with trusted service providers. | High | Provides user feedback and generates platform revenue. | Preference for traditional booking methods and lack of trust in new platforms.
The Groom Room by Steve | User | Client |  | Expects increased sales from successful bookings, better market exposure, and comprehensible business reports. | High | Provides service listings and essential feedback for B2B features. | Reluctant to change established manual business processes.
Feliz Angelica Salting | Management | Team Lead / Release Manager / Developer / Sales & Marketing Staff | Project Manager, Development Team, QA, and Project Advisers | Ensure stable builds, meet sprint goals, and oversee deployment and build brand awareness. | High | Managing internal workflow, version control/release, coding, and social media promotion. | Technical blockers during deployment and unrealistic deadlines.
Atasha Frances Gayle Doria | Development Team | Lead Developer/ Sales & Marketing Staff | Project Manager, Release Manager, & Project Advisers | Develop a system that passes all the acceptance criteria and build brand awareness. | High | Develops/leads platform architecture, coding, and promoting the system on social media. | Unclear requirements, lack of time for development, and limited budget.
Michelle Reina Pineda | Testing Team | Lead Quality Assurance/ Sales & Marketing Staff | Project Manager, Release Manager, & Project Advisers | Ensure the system is bug-free, meets all requirements and build brand awareness. | High | Leads system testing, bug reporting, and promoting the system on social media. | Unclear acceptance criteria, lack of time for thorough testing, and limited budget.
Lalainne Andaya | Management | Project Manager / Developer / Sales & Marketing Staff | Lead Developer & Project Advisers | Successfully project delivery within scope and timeline, while achieving high-level stakeholder satisfaction. | High | Strategic planning, timeline management, and resource coordination. | Last-minute changes and limited budget.
Developers | Development Team | Frontend and Backend Developers | Lead Developer, Project Manager, Release Manager, & Project Advisers | Develop the system's features and meet all technical goals. | High | Writes code, fix bugs, and integrates the database. | Unclear requirements, limited budget for development, and technical challenges with minimal development time.
Mr. Gonzalo Gumogda | Asia Pacific College | Project Adviser | Project Manager and Team Lead | Guide the students towards successful project completion. | High | Guides the Management, Development, and QA Team in each SDLC phase, while validating the project's progress. | Team's lack of experience.
Mr. Gil Ballesca | Asia Pacific College | Project Co-Adviser | Project Manager and Team Lead | Guides the student towards successful project completion, specifically within their area of expertise. | Medium | Provides specialized support to the Management, Development, and QA Team in each SDLC phase, while validating the project's progress. | Team's lack of experience.
Competitors |  | External Influence |  | Continuously compete in the growing market, providing opportunities for innovation. | Low | Pushes the team to innovate and provide a better experience to users. | Established market presence with ample resources.

## Sheet1
1 | 6790 | 1 | 56.9 | 5690 | 1100 |  | 5690 | 0
1.85 |  | 0.2 |  |  | 11 | 2.85
0.2 |  | 0.25 |  |  | 13 | 0.2
0.25 |  | 0.8 |  |  |  | 0.25
1.07 |  | 0.12 |  |  |  | 1.07
0.12 |  | 1 |  |  |  | 0.12
1 |  | 0.33 |  |  |  | 1
0.33 |  | 1 |  |  |  | 0.33
1 |  | 0.92 |  |  |  | 1
0.92 |  | 0.25 |  |  |  | 0.92
0.25 |  | 0.25 |  |  |  | 0.25
0.25 |  | 0.27 |  |  |  | 0.25
0.25 |  | 0.5 |  |  |  | 0.25
0.5 |  | 0.2 |  |  |  | 0.5
0.2 |  | 0.85 |  |  |  | 0.2
0.85 |  | 0.23 |  |  |  | 0.85
0.23 |  | 0.82 |  |  |  | 0.23
0.82 |  | 0.2 |  |  |  | 0.82
0.2 |  | 2 |  |  |  | 0.2
2 |  | 0.55 |  |  |  | 2
0 |  | 0.15 |  |  |  | 0
0.37 |  | 0.07 |  |  |  | 0.37
0.07 |  | 0.25 |  |  |  | 0.07
0.25 |  | 0.18 |  |  |  | 0.25
0.18 |  | 1 |  |  |  | 0.18
1 |  | 3.5 |  |  |  | 1
3.5 |  | 1.5 |  |  |  | 3.5
1.5 |  | 0.18 |  |  |  | 1.5
0.18 |  | 1.17 |  |  |  | 0.18
1.17 |  | 0.65 |  |  |  | 1.17
2.4 |  | 1 |  |  |  | 2.4
1 |  | 3 |  |  |  | 1
1.27 |  | 2.27 |  |  |  | 1.27
3 |  | 0.5 |  |  |  | 3
0 |  | 0.28 |  |  |  | 0
5.28 |  | 1.5 |  |  |  | 5.28
0.5 |  | 0.07 |  |  |  | 0.5
0.28 |  | 1.5 |  |  |  | 0.28
1.5 |  | 0.27 |  |  |  | 1.5
2.04 |  | 0.37 |  |  |  | 2.04
1.5 |  | 0.25 |  |  |  | 1.5
0.27 |  | 1 |  |  |  | 0.27
1.6 |  | 0.5 |  |  |  | 1.6
0.25 |  | 24 |  |  |  | 0.25
1 | [5 empty] | 1
0.5 | [5 empty] | 0.5
24 | [5 empty] | 13